## Sheet1
Golf Development Project Planning
User Stroies/To Do/Estimated Time | In Progress | Issues | Done/Actual Time | Final Test
Setting up Virtual environment and Django (30 minutes) | Creating Models in models.py User Account Information(30 Minutes) 10/26 |  | Setting up Virtual environment and Django (15 minutes) | Approved
Creating Models in models.py User Account Information(30 Minutes) |  |  | Creating Models in models.py User Account Information(30 Minutes) 10/27 | Approved
Creating Models in models.py Personal Record(1 hour), Leaderboard(1 hour) |  | Swapped leadboard to view all notebook and personal record is now notebook but for all invdivuals | Creating Models in models.py Notebook(20 mins), View all notebook(20 mins) 10/29 | Approved
Creating Models in models.py Courses, Holes, Rounds (Combine up to 2 hours) | Creating Models in models.py Courses, Holes, Rounds (Combine up to 2 hours)11/01 | Sprint 1 only needs Rounds | Models for Rounds( 15minutes)11/01 | Apporved for sprint1
Creating URLs pattern in Urls.py User account( 1 hour) |  | Change from user account to golfer | Creating URLs pattern in Urls.py Golfer account( 40 minutes)11/01 | approved
Creating URLs pattern in Urls.py Course Selection, Hole Selection, Hole Par Amount, Scoring summary (30-45) | Creating URLs pattern in Urls.py Course Selection, Hole Selection, Hole Par Amount, Scoring summary 10/31 | Sprint 1 only needs Scoring Summary | URLS pattern Scoring summary (15 minutes)11/01 | approved for sprint 1
Creating URLs pattern in Urls.py Personal record, leaderboard (1-2 hours each) |  | Changed to notebook_detail and notebook_list | Created URLs notebook_detail and notebook_list (40 mins)11/02 | Approved
Creating Templates(HTML/CSS/BOOTSTRAP) in Templates.py menu/homepage (1-2 hours) |  |  | Creating Templates(HTML/CSS/BOOTSTRAP) in Templates.py menu/homepage (20 minutes) 11/02 | Approved
Creating Templates in Templates.py User profile ( 1 hour) Admin profile (1.5hours) |  | Formatting issues, screen size not adjusting | Creating Templates in Templates.py User profile Admin profile (1 hour)11/02 | Approved
Creating Templates in Templates.py Leaderboard (1-2 hours) |  | Formatting issues, screen size not adjusting, rendering notebooks in correct format | Creating Templates in Templates.py Leaderboard (2 hours) | Approved
Create Admin profile in admin.py allowing to delete and update profiles ( 30-45 minutes ) |  | Create Admin profile in admin.py allowing to delete/update profiles suppose to be in the views.py not admin | Create Admin profile in admin.py/ create views to delete and update profiles ( 2hours ) | Approved
Sprint Backlog 1
Sprint Backlog (User stories for Sprint 1 ): Admin Profile Setup Leaderboard View for Users Users Record Scores Admin View of User Scores |  | (Step 1): Setup Django environment and dependencies. (Step 2): Implement Admin profile setup - model, views, URLs. (Step 3): Design and layout for leaderboard view. (Step 4): Item detail view for users to record scores - URLs, views, html. (Step 5): Admin view to check and verify user score