## Sheet1
Golf Development Project Planning
User Stroies/To Do/Estimated Time | In Progress | Issues | Done/Actual Time | Final Test
Setting up Virtual environment and Django (30 minutes) | Creating Models in models.py User Account Information(30 Minutes) 10/26 |  | Setting up Virtual environment and Django (15 minutes)
Creating Models in models.py User Account Information(30 Minutes)
Creating Models in models.py Personal Record(1 hour), Leaderboard(1 hour)
Creating Models in models.py Courses, Holes, Rounds (Combine up to 2 hours)
Creating URLs pattern in Urls.py User account( 1 hour)
Creating URLs pattern in Urls.py Course Selection, Hole Selection, Hole Par Amount, Scoring summary (30-45)
Creating URLs pattern in Urls.py Personal record, leaderboard (1-2 hours each)
Creating Templates(HTML/CSS/BOOTSTRAP) in Templates.py menu/homepage (1-2 hours)
Creating Templates in Templates.py User profile ( 1 hour) Admin profile (1.5hours)
Creating Templates in Templates.py Leaderboard (1-2 hours)
Create Admin profile in admin.py allowing o delete and update profiles ( 30-45 minutes )
Sprint Backlog 1
Sprint Backlog (User stories for Sprint 1): Admin Profile Setup Leaderboard View for Users Users Record Scores Admin View of User Scores |  | (Step 1): Setup Django environment and dependencies. (Step 2): Implement Admin profile setup - model, views, URLs. (Step 3): Design and layout for leaderboard view. (Step 4): Item detail view for users to record scores - URLs, views, html. (Step 5): Admin view to check and verify user score